Instructions

1.	Use this form for periodic progress reports on objectives of the District Strategic Plan.

2.	Complete the Preparer table.

3.	Complete the information in the Goal and Objective tables, which may be copied and pasted as needed to accommodate all the goals and all the objectives under each goal on which you are reporting.

a.	Please enter a Revised Timeline/Deadline only if the analysis of progress to date on that objective clearly demonstrates the need for it.

b.	If any Actions/Activities and/or Measurements/Documentation of Progress suggested by the original planning group have been pre-entered, you may edit them as needed.

c.	List all major Actions/Activities that are completed, underway, scheduled, or planned.  If you need space for more actions/activities, add lines as needed to the table.

d.	In the Status Code column, indicate whether each action/activity is Completed, Underway, Scheduled, or Planned.*

e.	In the Progress Description column, briefly describe your progress on each action/activity that is Underway.

f.	In the Measurements/Documentation of Progress column, identify the written evidence you will use to demonstrate your progress on each action/activity.

| Name of Preparer | Date |
| --- | --- |
| Alisa Sparkia Moore, Chair; District Outreach and Marketing Committee | 12.23.10 |

| Goal | 6.1.Enhance the district’s value and image in the communities |
| --- | --- |

| Objective |  | Original Timeline/Deadline | Revised Timeline/Deadline |  | Point Person or Group |
| --- | --- | --- | --- | --- | --- |
| 6.1.1 Develop a comprehensive district marketing and outreach plan, coordinated with those of the colleges, to raise the communities’ awareness of education and training services |  | Spring 2011- Fall 2011 |  |  | Alisa Moore |
| Actions/Activities (Edit as needed to reflect actual accomplishments or plans) | Status Code* | Progress Description |  | Measurements/Documentation of Progress (Edit as needed to match Actions/Activities) |  |
| Establish Committee | C | Expanded to include students, community members, outreach staff from campuses |  |  |  |
| Conduct a community audit or survey: Employees, Students, Community Summarize current efforts in marketing/outreach across District | U | Survey of the employees will take place in January; will discuss student survey at January committee meeting |  |  |  |
| Develop the plan | U | No current campus marketing plans exist; have to create alternatives. Plan must build on what is currently being done, focus on gaps identified, and incorporate the wide swings in enrollment experienced by the campuses |  |  |  |
| Implement the plan |  |  |  |  |  |
| Evaluate the Effectiveness of the plan |  |  |  |  |  |
| Develop a Message Deck to ensure consistency in district communications to the public |  |  |  |  |  |