Instructions

1.	Use this form for periodic progress reports on objectives of the District Strategic Plan.

2.	Complete the Preparer table.

3.	Complete the information in the Goal and Objective tables, which may be copied and pasted as needed to accommodate all the goals and all the objectives under each goal on which you are reporting.

a.	Please enter a Revised Timeline/Deadline only if the analysis of progress to date on that objective clearly demonstrates the need for it.

b.	If any Actions/Activities and/or Measurements/Documentation of Progress suggested by the original planning group have been pre-entered, you may edit them as needed.

c.	List all major Actions/Activities that are completed, underway, scheduled, or planned.  If you need space for more actions/activities, add lines as needed to the table.

d.	In the Status Code column, indicate whether each action/activity is Completed, Underway, Scheduled, or Planned.*

e.	In the Progress Description column, briefly describe your progress on each action/activity that is Underway.

f.	In the Measurements/Documentation of Progress column, identify the written evidence you will use to demonstrate your progress on each action/activity.

| Name of Preparer | Date |
| --- | --- |
| Alisa Sparkia Moore, Chair; District Outreach and Marketing Committee | 01.27.12 |

| Goal | 6.1.Enhance the district’s value and image in the communities |
| --- | --- |

| Objective | Original Timeline/Deadline | Revised Timeline/Deadline | Point Person or Group |
| --- | --- | --- | --- |
| 6.1.1 Develop a comprehensive district marketing and outreach plan, coordinated with those of the colleges, to raise the communities’ awareness of education and training services | Spring 2011- Fall 2011 |  | Alisa Moore |
| Actions/Activities (Edit as needed to reflect actual accomplishments or plans) | Status Code* | Progress Description | Measurements/Documentation of Progress (Edit as needed to match Actions/Activities) |
| Survey Students | C | Survey has been submitted to students, still open |  |
| Survey Employers | U | Survey drafted; open; trying to find other ways to expand the dissemination |  |
| Survey Community | P | Considering various ways to reach appropriate, representative and varied members of the community, as well as what questions to ask. |  |
| Collect Data on Outreach done by each unit in the 2010-11 year as a baseline | U | Survey drafted, to be implemented prior to next committee meeting (Dec. 8) |  |
| Develop Plan | U | Will complete draft by end of Spring semester |  |
| Implement Plan |  |  |  |
| Evaluate Effectiveness of Plan |  |  |  |

Consider/ Create Message Deck